## Table 1
| Task (for searches starting in 2014 and beyond) | Fall Minister Start | Winter Minister Start
Direction-Finding
1. | Board arranges for visits of - District Executive (DE)/Regional Staff Liaison - Ministerial Settlement Representative (MSR) - District Compensation Consultant | Jan-Apr | Jul-Dec
2. | Provide requested information to the MSR (first consultation) | Jan-Jun | Jul-Dec
2a. | Meet with MSR (first consultation) | Jan-Jun | Jul-Dec
3. | Board plan search committee process | Jan-Jun | Jul-Dec
4. | Board adopt search committee budget | Jan-Jun | Jul-Dec
5. | Board conduct congregation’s selection of search committee | Jan-Jun | Jul-Dec
5a. | Search Committee formed | May-Aug | Nov-Feb
Self-Study
6. | Search committee familiarize itself with Transitions Website and the Ministerial Settlement System | Jun-Sep | Dec-Mar
7. | SC read/print out a copy of the Settlement Handbook and the Resource Guide for every member | Jun-Sep | Dec-Mar
8. | Search committee (SC) provide requested info to MSR on MSR 1 form. | Jun-Sep | Dec-Mar
9. | Meet with MSR (second consultation) | Jun-Sep | Dec-Mar
10. | SC go on facilitated overnight retreat | Jun-Sep | Dec-Mar
11. | SC select chair (and Transitions Office Contact), allocate tasks, establish timeline | Jun-Sep | Dec-Mar
12. | Board select negotiating team to recommend ministerial compensation package and draft agreement | Jun-Sep | Dec-Mar
13. | SC gather information by cottage meeting, survey, interviews | Jun-Sep | Dec-Mar
14. | SC schedule Beyond Categorical Thinking (BCT) workshop for cong. and SC | Jun-Sep | Dec-Mar
15. | SC compose congregational record (CR) | Jun-Oct | Jan-Apr
16. | SC begin compilation of search website or electronic informational packet for exchange with interested ministers | Jun-Oct | Jan-Apr
17. | Negotiating team present recommended compensation package and draft agreement to Board | Jun-Oct | Jan-Apr
18. | SC Sponsors Beyond Categorical Thinking Workshop | Aug-Dec | Mar-Jun
Framing the Search
19. | SC set up neutral pulpit arrangements with nearby congregations | Jul-Oct | Jan-Apr
20. | SC create, distribute, and analyze results of congregational survey and other information-gathering | Jul-Nov | Jan-May
21. | Board tender approved compensation package and draft agreement to search committee (if a vote by the Cong. is required, allow time for it) | Jul-Nov | Jan-May
22. | SC prepare information packet, including draft agreement and survey results. Make copies for potential candidates. Send copy to MSR for review | Jul-Nov | Jan-May
23. | SC complete online Application for Minister (Option 3 in Settlement System - includes compensation figures) | Nov 30 | May 31
24. | SC complete online CR (Option 1 in Settlement System) | Nov 30 | May 31
Open for Business
25. | SC request MSR to give go-ahead for Transitions to unveil CR; follow up to make sure the unveiling occurs by | Nov 30 | May 31
26. | SC meet with MSR- third consultancy (often by conference call) and no later than | Jan 2 | Jul 1
27. | SC requests access to Ministerial Records (MRs) when the following are in order, ideally no later than - Electronic copies of survey results, draft agreement, compensation calculator form received by Transitions Office (see website for form) - Informational website or electronic packet reviewed by MSR - MSR’s third consultancy is imminent | Jan 3 | Jul 2
28. | SC call interested ministers, exchange packets with those whose interest it reciprocates | Jan- Early Feb | Jul-Aug
29. | SC receive, circulate, and evaluate ministers’ packets, conduct group phone interviews, interview named references | Jan- Early Feb | Jul-Aug
30. | Transitions make available MRs of additional interested ministers as manifested | Jan- Early Feb | Jul-Aug
31. | SC selcect and schedule three of four pre-candidates for pre- candidating weekends including neutral pulpits | Jan- Early Feb | Jul-Aug
32. | SC informs Transitions Office of pre-candidates and requests interpretive file summaries (2 week turnaround) | Feb | Aug
33. | SC, with the precandidates’ acknowledgement, interview developed references in congregations in which the pre-candidates have previously serve and with previous employers and named references in current congregation | Feb-Mar | Aug-Sep
Pre-Candidating
34. | Pre-candidating weekends! | Feb-Mar | Aug-Sep
Selection
35. | SC make offer to first choice for candidate contigent on satisfactory criminal background check and interviews of developed references in current congregation/employment no earlier than noon Eastern time | March 29 2018 | First Thurs. of Oct
36. | SC with the proposed candidate’s acknowledgementinterview developed references in current congregation or employment | Apr | Oct
37. | SC conduct criminal background check on proposed candidate | Apr | Oct
38. | Negotiating team conclude ministerial agreement with candidate, including compensation matters, subject if necessary to contigencies in step 35 | Apr | Oct
39. | SC conclude background check and reference interviews | Apr | Oct
40. | Board and candidate execute ministry agreement subject to extension of call by congregation and acceptance by candidate | Apr | Oct
41. | Board announces candidacy (only after completion of background check and contract negotiations | Apr | Oct
Candidating Week
42. | Congregation extends call and ministers accepts | Apr-May | Oct-Nov
43. | SC submits Notice of Call to Transitions | Apr-May | Oct-Nov
Minister Arrives
44. | Minister Arrives | Aug-Sep | Jan-Feb